## State of the Product Memo

To: Alex Chen, Platform Engineering Lead
From: Rohan Tejaswi, Senior PM (Week 1)
Date: April 2026
Re: Current health, top risks, and the next bet

Alex — I've been through the codebase, issues, PRs, Grafana metrics, and Slack history this week. Here's my honest read. I'm not softening anything.

### Current Health: The Numbers

| Metric | Jan 1 | Apr 5 | Target | Direction |
| --- | --- | --- | --- | --- |
| Median turnaround | 48 hrs | 55 hrs | 28 hrs | ↑ Worsening |
| AI extraction rate | 0% (not live) | 62% | 80% | → Flat 6 wks |
| Daily request volume | ~200/day | ~340/day | — | ↑ +70% |
| Active reviewers | 5 | 3 | — | ↓ Dropping |

Volume growth overwhelmed the February extraction gains within 2 weeks. At 340/day with 3 reviewers and 62% extraction, each reviewer handles ~43 fully manual cases daily. That's unsustainable, and it's getting worse.

### Risk 1: PHI Compliance — One Incident Response Step Away

queries.rs:42 logs decrypted patient names at debug level:

log::debug!("Fetched auth request for patient: {} {}",    
        request.patient_first_name, request.patient_last_name);

At RUST_LOG=info this isn't leaking. But the API pod OOM-crashes every ~48 hours (Issue #10), and the natural debugging step is RUST_LOG=debug. If that happens before PR #54 merges, patient names go into plaintext logs — that's a HIPAA incident report. PR #54 is a 15-minute code review. It should be done today.

### Risk 2: API Stability & Configuration Drift

The API pod hits its 128Mi limit every 24–48 hours, OOM kills, and restarts (Grafana P4: P95 spikes to 6–8s on restart; Issue #10; Slack Thread #1). Compounding: DATABASE_MAX_CONNECTIONS=10 is parsed at mod.rs:5-13 but never applied to the pool — peak-load behavior is unpredictable. Stopgap: bump limits to 256Mi/512Mi in values.yaml. HPA (Issue #12) is the right longer-term fix.

### Risk 3: VP Escalation — 18 Days, Zero Response

Slack Thread #5, March 28: VP Clinical Ops asked about auto-approve. No response. PR #53 raises four product questions — I'm the product owner now and I'll answer them:

- CPT list: PR #53's list (80053, 80061, 85025, 71046, 93000) is directionally correct, pending clinical ops validation.

- Threshold: Exact CPT match + urgency_level = "routine" + extraction completeness check. No ML score needed — the ML Scoring Service doesn't exist.

- Audit trail: Yes, via migration 009's auto_approve_log table.

- Human override: Yes, a requires_manual_review flag for edge cases.

### What's Being Ignored

- FIFO queue: queries.rs:69-72, ~2 hours of work, immediate reviewer impact (Slack Thread #3, Issues #5, #26).

- Analytics crash: analytics.rs:20-29 is a todo!() — if the VP hits /turnaround-times, the API pod panics.

- Pipeline CI: Dark since December. Issue #16 (wrong LLM model running undetected) happened because nothing caught the config mismatch.

### Recommended Next Bet: 30-Day Throughput Unlock

- Week 1 — Safety: Merge PR #54 (PHI fix), bump K8s limits to 256Mi/512Mi, re-enable pipeline CI

- Week 2 — Capacity: Ship urgency sort (Issue #26), resolve PR #47 conflict, clinical ops CPT validation session

- Week 3 — Pipeline: LLM retry logic (Issue #11), merge PR #53 (auto-approve) once criteria confirmed

- Week 4 — Measurement: Rotated PDF preprocessing (Issue #6), materialized views for analytics (Issue #19)

Target: 82% extraction by end of April, auto-approve live, real path to 28-hour turnaround by Q2. The math only works if we start removing the ceiling now.

What do you need from me to make this happen?

— Rohan