## Slide 1
MACHINIFY — SENIOR PM TAKE-HOME
Auth Review Assistant
Week 1 Findings & 30-Day Recommendation
55 hrs
Current Turnaround
Target: 28 hrs ↑ Getting worse
62%
AI Extraction Rate
Flat for 6 weeks
0
Auto-Approves Shipped
Q1 target: 30% of volume
Rohan | April 2026

## Slide 2
WHAT I FOUND — READING THE CODE, NOT THE README
The README lies. Here's what the code actually says.
👻 ML Scoring Service: Doesn't Exist
README architecture diagram shows it live and feeding confidence scores. Issue #15: the ml_confidence_score column in the DB has never been written to. The service was never built.
🔓 PHI in Debug Logs — PR #54 Unreviewed
Patient names logged at debug level in crates/core/src/data/queries.rs:38. Safe at info level today. One RUST_LOG=debug in production = HIPAA incident.
📦 Approved PR Unmerged for 45 Days
PR #47 (OCR caching, +30% efficiency) approved March 2. One merge conflict. Sarah offered to fix it twice. No response. Zero new dev work required to ship this.
🚫 Pipeline CI Disabled Since December
.github/workflows/pipeline-test.yaml.disabled — 4 months of Python changes shipped untested. Issue #16: a production incident resulted (wrong LLM model running undetected).
Sources: ISSUES.md #15, #16 · PULL-REQUESTS.md PR #47, #54 · crates/core/src/data/queries.rs:38 · .github/workflows/

## Slide 3
PRODUCTION METRICS — 90 DAYS (JAN–APR 2026)
Every KR is red or yellow. The AI is live — but it's not working hard enough.
KR1
Reduce median turnaround: 48hrs → 28hrs
🔴 RED Current: 55 hrs Target: 28 hrs
15% WORSE than baseline. Volume grew 70% in 90 days. AI gains absorbed within 2 weeks of launch.
KR2
80% AI extraction success rate
🟡 YELLOW Current: 62% Target: 80%
Flat for 6 weeks. Blockers: PR #47 unmerged, no LLM retry (Issue #11), rotated PDFs (Issue #6).
KR3
Ship auto-approve for routine procedure codes
🔴 RED Current: Not shipped Target: 30% of volume
Draft PR #53 open — waiting for product criteria. VP escalated March 28. No PM response.
⚠️ Only 3 of 5 reviewers are active. Combined with 70% volume growth, this explains the turnaround regression — independent of the AI pipeline. (Grafana Panel 6)

## Slide 4
RECOMMENDED NEXT BET — 30-DAY PIPELINE HARDENING SPRINT
Three workstreams. No new features. Just unblocking what's already done.
🔥 This Week
Review & merge PR #54
PHI fix — 15 min code review
Compliance fire, not a feature
Resolve conflict on PR #47
OCR caching already approved
Sarah resolves, ~30 min
Re-enable pipeline CI
PM-owned: I spec the mock
Engineering re-enables tests
📋 Week 2–3
Sort queue by urgency
Issue #26: ORDER BY urgency_level
~2 hrs dev, huge reviewer win
LLM retry logic
Issue #11: exponential backoff
~1 day work, fixes 6% of failures
Auto-approve criteria session
Clinical ops validates CPT list
Unblocks PR #53 to ship
📈 Week 4
Merge PR #53 (auto-approve)
Once criteria confirmed
Closes VP Clinical Ops escalation
Bump K8s memory limits
Issue #12: 256Mi/512Mi
Eliminates OOM restart cycle
Materialized views for analytics
Issue #19: unblocks dashboards
No data warehouse needed yet
Expected outcome: Extraction 62% → ~82–85% · Auto-approve ships · VP escalation closed · Path to 28-hr target by Q2

## Slide 5
PROTOTYPE BUILT · WHAT I NEED FROM YOU
🛠 What I Built: confidence_gate.py
pipeline/src/confidence_gate.py
The missing product layer between Draft PR #53 (auto-approve endpoint) and the 4 unanswered product questions Alex left in the PR.
Evaluates extracted auth requests → returns:
AUTO_APPROVE · MANUAL_REVIEW · ESCALATE
Full audit record output → auto_approve_log table (PR #53, migration 009). All decisions traceable.
5/5 test cases pass. Run it:
python -m src.confidence_gate --test
🙋 What I Need from You
Engineering (Alex)
30 mins to unblock PR #47 (Sarah can resolve the conflict). And: is 256Mi enough to stop OOM kills while we profile, or do we need to profile first?
Clinical Ops
One 45-min session to validate the CPT auto-approve list in PR #53 (80053, 80061, 85025, 71046, 93000). Right list? What's missing?
Legal / Compliance
Has auto-approve been reviewed for state prior auth regulations? PRD flagged it. No evidence it happened. Blocker before PR #53 ships.
Manager
Why did 2 of 5 reviewers go inactive in February? If it's attrition, the 28-hour target math needs to be re-baselined.
Rohan | Machinify Senior PM Take-Home | April 2026